Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date | 01 September 2026 |
| --- | --- |
| Team ID | Individual Project |
| Project Name | Software Installation Request Automation in ServiceNow |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

Use the below template to create product backlog and sprint schedule.

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Service Catalog Setup | USN-1 | As an individual project owner, I can create an Update Set to capture the project configuration changes. | 2 | High | Individual |
| Sprint-1 |  | USN-2 | As an employee, I can submit a standardized Software Installation Request catalog item. | 3 | High | Individual |
| Sprint-1 |  | USN-3 | As a requester, I can enter Software Name, Version Required, License Justification, and Urgency. | 5 | High | Individual |
| Sprint-1 |  | USN-4 | As a requester, I can test the catalog item and verify that the submitted request is created correctly. | 2 | High | Individual |
| Sprint-1 | Request Tracking | USN-5 | As an administrator, I can verify the request and requested-item records for the submitted catalog request. | 3 | Medium | Individual |
| Sprint-1 |  | USN-6 | As an administrator, I can configure basic requester notifications for the request lifecycle. | 5 | Medium | Individual |
| Sprint-2 | Workflow & Fulfillment | USN-7 | As an administrator, I can create an automation flow/workflow for the software installation request. | 5 | High | Individual |
| Sprint-2 |  | USN-8 | As an approver, I can receive and process the approval for a software installation request. | 3 | High | Individual |
| Sprint-2 |  | USN-9 | As an IT support member, I can receive an automatically created fulfillment task. | 5 | High | Individual |
| Sprint-2 |  | USN-10 | As an administrator, I can attach the workflow/flow to the Software Installation Request catalog item. | 2 | High | Individual |
| Sprint-2 |  | USN-11 | As an IT support member, I can update the task state from Open to Work in Progress to Completed. | 3 | Medium | Individual |
| Sprint-2 |  | USN-12 | As a requester, I can receive progress notifications during approval and fulfillment. | 2 | Medium | Individual |
| Sprint-3 | Exception Handling & Business Rules | USN-13 | As an administrator, I can validate sc_request and sc_req_item records after request submission. | 3 | High | Individual |
| Sprint-3 |  | USN-14 | As an administrator, I can create a Business Rule that detects a software request placed On Hold. | 5 | High | Individual |
| Sprint-3 |  | USN-15 | As an administrator, I can create an incident automatically when a license shortage prevents fulfillment. | 5 | High | Individual |
| Sprint-3 |  | USN-16 | As an administrator, I can configure SLA tracking for timely software request fulfillment. | 3 | Medium | Individual |
| Sprint-3 |  | USN-17 | As an administrator, I can test the license shortage and incident-creation scenario. | 2 | Medium | Individual |
| Sprint-3 |  | USN-18 | As an administrator, I can review request and fulfillment records for reporting purposes. | 2 | Low | Individual |
| Sprint-4 | Testing & Deployment | USN-19 | As an administrator, I can execute end-to-end testing of catalog, approval, task, notification, and exception handling. | 5 | High | Individual |
| Sprint-4 |  | USN-20 | As an administrator, I can complete the project Update Set after configuration is finalized. | 2 | High | Individual |
| Sprint-4 |  | USN-21 | As an administrator, I can export the completed Update Set as XML. | 2 | High | Individual |
| Sprint-4 |  | USN-22 | As an administrator, I can retrieve the Update Set in another instance for deployment testing. | 3 | High | Individual |
| Sprint-4 |  | USN-23 | As an administrator, I can preview and commit the Update Set without missing configuration elements. | 3 | High | Individual |
| Sprint-4 |  | USN-24 | As an administrator, I can validate that all transferred configurations work correctly after deployment. | 5 | High | Individual |

Project Tracker, Velocity & Burndown Chart: (4 Marks)

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 20 | 6 Days | 09 Aug2026 | 14 Aug2026 | 20 | 14 Aug 2026 |
| Sprint-2 | 20 | 6 Days | 15 Aug2026 | 20 Aug2026 | 20 | 20 Aug 2026 |
| Sprint-3 | 20 | 6 Days | 21 Aug2026 | 26 Aug2026 | 20 | 26 Aug 2026 |
| Sprint-4 | 20 | 6 Days | 27 Aug2026 | 01 Sep2026 | 20 | 01 Sep 2026 |

Velocity:

Imagine we have a 6-day sprint duration, and the velocity of the individual project is 20 story points per sprint. Let’s calculate the average velocity (AV) per iteration unit (story points per day).

Total Story Points = 20 + 20 + 20 + 20 = 80

Number of Sprints = 4

Velocity = 80 / 4 = 20 Story Points per Sprint

Average Velocity per Day = 20 / 6 = 3.33 Story Points per Day

Burndown Chart:

A burn down chart is a graphical representation of work left to do versus time. It is often used in agile software development methodologies such as Scrum. However, burn down charts can be applied to any project containing measurable progress over time.

Planning Summary: The backlog is divided into four planned Sprints. Sprint 1 focuses on Service Catalog setup and request tracking; Sprint 2 focuses on workflow and fulfillment; Sprint 3 covers Business Rules, SLA and exception handling; Sprint 4 covers end-to-end testing and Update Set deployment.

Reference: https://www.atlassian.com/agile/project-management